WORKFORCE disABILITY EQUALITY STANDARD – ACTION PLAN 2020/21

| WDES indicator | current position | action |  | lead | timescale | National and trust strategy alignment | outcome | action RAG rating* |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1) Percentage of staff in AfC pay-bands or medical and dental subgroups and very senior managers (including Executive Board members) compared with the percentage of staff in the overall workforce. | Disabled colleagues account for 5% of the overall workforce in the Trust. This compares with national picture of 18% of disabled population in employment. | Overhaul the recruitment & selection processes to ensure they enable disabled people to apply for roles and a fair process for selection |  | Deputy Director of People and OD /Head of People Resourcing | March 21 | Networks feedback We are the NHS: People Plan 2020/21 – action for us all SCHFT Trust People Plan 20/22 Please take a look at the attached document Trust Caring Together Strategy 20/25 new strategy and values for 2020 – 25. Inclusion Strategy December 2020 Trust Education & Training Plan April 2021 NHS Long Term Plan | Increase representation of disabled colleagues across all grades and particularly at leadership level Target: Disabled colleagues as a proportion of all colleagues to be representative of Sheffield working population by March 2025 Target: Senior manager positions (8a+) to be representative of SC workforce by March 2025 Target: Board/NED/Governor recruitment is representative of SC workforce by March 2025 |  | x |  |
|  |  | - Review compliance with Disability Confident Employer (level 2) - set out steps to attain level 3: Disability Confident Leader |  | Deputy Director of People and OD | Mar 21 |  |  |  | X |  |
|  |  | Review data kept on ESR and validation of data to ensure its accurate and reflective |  | HR Manager (WFI) | April 21 and then annually |  |  |  | X |  |
|  |  | DisAbled colleagues trained to sit on recruitment panels (with equal voice) band 7 and upwards |  | Head of HR | July 21 |  |  |  | X |  |
|  |  | DisAbility Network input into Education and Training Plan to ensure disabled colleague support included. |  | Head of Learning and OD | Tbc |  |  |  | X |  |
| 2) Relative likelihood of non-disabled staff compared to Disabled staff being appointed from shortlisting across all posts. | 2019 – 1.98 2020 – 1.92 | All recruitment panel members to undergo bias and equality awareness (mandatory) [Board recruitment awareness blue print] |  | Head of Learning and OD/Head of HR | Mar 22 | We are the NHS: People Plan 2020/21 – action for us all SCHFT Trust People Plan 20/22 Please take a look at the attached document Trust Caring Together Strategy 20/25 new strategy and values for 2020 – 25. Inclusion Strategy December 2020 Trust Education & Training Plan April 2021 | Increase in disabled shortlisted candidates being appointed. |  | X |  |
|  |  | Recruitment process overhaul, scrutiny, checks and balances, positive action tie breaker rule introduced. Recruitment decision escalation established in recruitment process. |  | Deputy Director of People and OD | Mar 21 |  |  |  | x |  |
| 3) Relative likelihood of Disabled staff compared to non-disabled staff entering the formal capability process, as measured by entry into the formal capability procedure. | 2019 – 9.05 2020 - 0.00 | Overhaul of the capability process: formal capability process as a last resort [*disciplinary and attendance at work policies also to be reviewed and circulated to the disability network group for review as part of process] |  | Head of HR | Mar 21 | A Fair Experience for All | Fairer process and lower capability rate for all |  | x |  |
| 4a) Percentage of Disabled staff compared to non-disabled staff experiencing harassment, bullying or abuse from |  |  |  |  |  |  |  |  |  |  |
| i) Patients/Service users, their relatives or other members of the public | 2019 - D - 23.1% ND - 19.0% 2020 - D - 29.2% ND - 19.0% | Civility/respect campaign to the public about behaviour towards our colleagues [‘what happens what you attack my daddy] including guidance for colleagues, bystanders, reporting and escalation, police involvement and support mechanisms for those who receive adverse experience | Deputy Director of POD/DNQ (cross organisational task group) |  | Launch of campaign March 21 | NHS/Trust People Plan NHS Violence Prevention and Reduction Standard | Fewer colleagues facing adverse experience, (nb increasing awareness may see rise in indicator before it reduces) |  | x |  |
| ii) Managers | 2019 D - 13.1% ND - 6.3% 2020 - D - 12.4% ND - 7.0% | Civility/respect campaign to managers about their behaviour towards fellow colleagues (as for i) above) | Deputy Director of POD (cross organisational task group) |  | Launch March 21 | NHS/Trust People Plan NHS Violence Prevention and Reduction Standard | Reduced number of disabled colleagues experiencing harassment, bullying or abuse from managers |  | x |  |
| iii) Other Colleagues | 2019 - D - 24.0% ND - 12.3% 2020 - D - 23.6% ND - 16.1% | Civility/respect campaign to colleagues in the Trust about their behaviour towards fellow colleagues (as for i) above) | Deputy Director of POD (cross organisational task group) |  | Launch March 21 |  | Reduced number of disabled colleagues experiencing harassment, bullying or abuse from their colleagues |  | x |  |
| 4b) Percentage of Disabled staff compared to non-disabled staff saying that the last time they experienced harassment, bullying or abuse at work, they or a colleague reported it. | 2019 - D - 42.7% ND - 47.9% 2020 - D - 49.4% ND - 50.8% | Campaign with regards to the reasons why these incidents need reporting and improve our communications with regards to the outcomes for all colleagues so they are aware it is worth reporting. | Deputy Director of POD/DNQ(as part of cross organisational task group) |  | Launch March 21 |  | An increase in all colleagues reporting these incidents. |  | x |  |
| 5) Percentage of Disabled staff compared to non-disabled staff believing that the Trust provides equal opportunities for career progression or promotion. | 2019 - D - 83.3% ND - 88.0% 2020 - D - 79.8% ND - 90.4% | Career progression and promotion experience, focus groups with disabled colleagues to ascertain lived experience Additional questions in staff surveys to understand perception. Scrutiny of career progression and promotion practices. Establish escalation process. | Head of Learning and OD/Head of HR Head of HR |  | June 21 Sep 21 |  |  |  | X X |  |
| 6) Percentage of Disabled staff compared to non-disabled staff saying that they have felt pressure from their manager to come to work, despite not feeling well enough to perform their duties | 2019 - D - 25.3% ND - 21.2% 2020 - D - 24.8% ND - 18.1% | Review the ‘attendance at work’ policy and its application which would include a review of the language used and the ‘triggers’. | Head of HR |  | March 21 |  | To reduce the number of colleagues across the Trust who are feeling pressured to attend work when feeling unable to do so | x |  |  |
| 7) Percentage of Disabled staff compared to non-disabled staff saying that they are satisfied with the extent to which their organisation values their work. | 2019 - D - 35.4% ND - 48.4% 2020 - D - 38.3% ND - 48.2% | - Additional staff survey questions for analysis , - Integrate into HWB conversations - Integrate into appraisal conversation | Head of HR Head of HR Head of Learning and OD |  | Sep 21 February 21 April 21 appraisal season | new strategy and values for 2020 – 25. | Increased percentage of colleagues feeling valued, and decrease in difference between ND and D colleague reporting |  | X x x |  |
| 8) Percentage of Disabled staff saying that their employer has made adequate adjustment(s) to enable them to carry out their work. | 2019 – 73.6% 2020 – 76.7% Target 100% | Review the attendance at work policy. Recognise that not all ‘disabled’ people are absent from work and include support etc in a ‘wellbeing policy’ To increase information to managers with regards to support in and outside of the Trust for colleagues, and adjustments. | Head of HR |  | Mar 21 |  | Survey results |  | x |  |
| 9a) The staff engagement score for Disabled staff, compared to non-disabled staff | 2019 - D - 6.8 ND - 7.2 2020 - D - 6.8 ND - 7.3 Disabled colleagues aren’t as engaged as non disabled colleagues but overall a good score | Refer to actions for other indicators to increase this score | Deputy Director of People and OD |  | Sep 21 | Inclusion and engagement strategy | Staff survey results |  | x |  |
| 9b) Has your Trust taken action to facilitate the voices of Disabled staff in your organisation to be heard? If yes, please provide at least one practical example of current action being taken in the relevant section of your WDES annual report. | Yes | The disability Network Group was established at the end of 2019. Improve attendance, input to other agendas, disability awareness | Deputy Director of People and OD |  | ongoing | Inclusion strategy | Network survey and staff survey results Trend of increasing participation and consistent representation of disabled colleagues voices |  | x | x |
| 10) Percentage difference between the organisation’s Board voting membership and its organisation’s overall workforce, disaggregated: • By voting membership of the Board. • By Executive membership of the Board | 0% disabled at date of data extraction | Every Board recruitment process to incorporate positive action plan to encourage disabled applicants. Publish diversity targets. | Director of POD/AD of Corporate Affairs February 21 |  | Ongoing | Trust inclusion strategy | Increased diversity of representation at Board level Board representation consistent with Trust wide representation |  | x | x |

*RAG rating explained: Green started and on track; amber to commence/started not on track with mitigations in place; red – started, not on track and mitigations not in place